## APQP-MATRIX (2)
ADVANCED PRODUCT QUALITY PLANNING - MATRIX
Purpose :- To define the rank of new development product & activitis & responbility for product development, Engineering change, process change of existing item.
Scope:- This is applicable from receipt of order to SOP of customer end.
Method :- Description rank of development and responsbilitity define as below .
CATEGORY FOR APQP | [11 empty] | LEGEND
A | Absolutely New Product / Part | E |  | Material Change | [8 empty] | Prime Responsibility
B | Similar Part | F |  | Machine Change | [8 empty] | Secondary Responsibility
C | Design Change | G |  | Plant Location Change/ Plant run after Long layoff ( More than 12 months) | [8 empty] | Activity required
D | Process Change / Layout Change | H |  | Supplier Change | [7 empty] | Blank | Activity Not required
S.No. | DESCRIPTION | CATEGORY | [7 empty] | Responsible Department | [6 empty] | Remarks
Phase - 1 ( Plan & Define Program ) |  | A | B | C | D | E | F | G | H | MKT | NPD | QA | PROD. | PUR. | HR | Top Mgt.
1 | Receipt of RFQ with drawing, sample and other information
2 | Formation of CFT
3 | Feasibility Study & Risk Analysis
4 | Preparation of prelimanary Process Flow diagram
5 | Cost Estimation and submission of quotation
6 | LOI / PO / Go-ahead from customer
7 | Preparation of APQP Timing plan
8 | Past defect history and lesson learning
9 | Preparation of bill of material (BOM)
10 | Select & develop supplier for RM / BOPs
11 | Identification of special Product & Process characteristics
Phase - II ( Product Design & Development )
12 | Identify new equipement & facility requirement
13 | Identify new Tool, Instrument, Gauge, fixture requirement
14 | Statutory & Regulatyory requirement identification
Phase - III ( Process Design & Development ) |  | Responsible Department QA: www.learnqctools.in
15 | Prepare of permanent PFD & process FMEA
16 | Prepration pre launch control plan
17 | Preparation of inspection standard ( Incoming, OPS, Final inspection standard) & WI etc
18 | Tool, Fixture & Gauge development or Tools reciept from supplier
19 | Inspection & validation of tool, fixture & gauge
20 | Provide training to concern person
21 | Sample T0 trial to be done
22 | T0 sample submission to the customer with layout inspection report
23 | Sample approval from customer
24 | Do correction if required
25 | Sample T1…..Tn trial
26 | T1….Tn sample submission and get apprroval from customer
Phase - IV ( Product & Process Validation )
27 | Training to concerned superviser operator and inspector for new / change part
28 | Pilot lot prepration with inspection report
29 | Carryout Product and process audit
30 | Carry out Meausrement system analysis
31 | Carry out processes capability study
32 | Prepare & finalize process documents ( PFD, PFMEA, CP, OPS & WI)
33 | Preparation of Packing Standard
34 | Submission of PPAP lot with PPAP documents
35 | Get PPAP approval from the customer with signed PSW/ PDI report
36 | SOP start at inhouse
37 | SOP start at customer end
38 | APQP sign off will be done by NPD head with CFT
Phase - V ( Feedback Assessment & Corrective action )
39 | Customer & Inhouse feedback analysis & corrective action ( summarize in PDCA sheet)
40 | Production, Quality & Delivery monitoring
41 | Handover to production
Rev No. | Description | CATEGORY G: Date; Responsible Department QA: Prepared by |  |  | Approved by
www.learnqctools.in